INDEPENDENT EDUCATION ADVISORY

Implementation Guide

From a standing start to an operating practice

Requirements, objectives and sequenced implementation for the business plan and the School Capability & Workload Diagnostic Matrix

Prepared for Beth Claydon & Sebastian Harper

August 2026  |  Version 1.0

“Happy Teachers = Happy Schools.”

# Contents

If this page appears blank, right-click below and choose Update Field to build the contents list.

Contents	1

How to use this guide	1

1. The starting position	1

1.1 What you actually have	1

1.2 What you do not have yet	1

1.3 The constraint that shapes everything	1

2. Objectives	1

Horizon 1 — Protect and establish (Months 0–3)	1

Horizon 2 — Build the minimum sellable product (Months 2–5)	1

Horizon 3 — Validate (Months 4–9)	1

Horizon 4 — Establish (Months 9–24)	1

3. Requirements register	1

3.1 Legal and structural	1

3.2 Financial	1

3.3 Compliance and risk	1

3.4 Employment and conflict of interest — Beth	1

3.5 Brand and market-facing	1

3.6 Product and intellectual property	1

3.7 Operational systems — Sebastian's lane	1

4. The diagnostic: from document to product	1

4.1 What V1 is, and what it is not	1

4.2 Layer 1 — the instrument	1

4.3 Layer 2 — the delivery protocol	1

4.4 Layer 3 — analysis	1

4.5 Layer 4 — the findings report	1

4.6 The conversion funnel	1

4.7 Version roadmap	1

5. Sequenced implementation	1

Phase 0 — Decide and protect (Weeks 1–3)	1

Phase 1 — Establish (Weeks 3–8)	1

Phase 2 — Build the minimum sellable product (Weeks 6–14)	1

Phase 3 — Pilot (Weeks 12–24)	1

Phase 4 — First paid engagements (Months 6–12)	1

Phase 5 — Productise (Months 12–24)	1

6. Commercial model	1

6.1 Establish the floor	1

6.2 Establish the ceiling	1

6.3 Revenue lines	1

6.4 Pricing principles	1

7. Risk register	1

7.2 Family governance	1

8. Decision register	1

Appendix A — Pre-launch checklist	1

Appendix B — Diagnostic engagement protocol	1

Appendix C — Questions for your advisers	1

For the accountant	1

For the lawyer	1

For the insurance broker	1

For Blue Card Services	1

Appendix D — Diagnostic core and module split	1

# How to use this guide

This guide converts two documents — the Educational Advisory Services business plan and the School Capability & Workload Diagnostic Matrix V1 — into an implementable sequence. It assumes nothing is set up yet.

It is organised so you can work through it in order:

- Sections 1–2 establish where you are starting from and what you are aiming at. Read these together, once.

- Section 3 is the requirements register — everything that must exist before you can trade safely. Work through it as a checklist.

- Section 4 turns the Diagnostic Matrix from a document into a deliverable product. This is the commercial core.

- Section 5 is the phased implementation plan with gates. Do not skip gates.

- Sections 6–7 cover pricing and risk.

- Section 8 is the decision register — nine decisions that block everything else. Start here if you only read one page.

A note on scope This guide sets out structure, sequence and the questions you need answered. It is not legal, tax, accounting or insurance advice, and it deliberately does not state registration thresholds, fees or premium figures — those change, and getting them from a professional who knows your circumstances is part of the plan rather than a detour from it. Section 3 and Appendix C are written so you can take them straight into a meeting with an accountant, a lawyer and an insurance broker.

# 1. The starting position

## 1.1 What you actually have

Two founders with complementary, non-overlapping assets. That is rarer and more valuable than it sounds — most founding pairs duplicate each other and then argue about the overlap.

### Beth — the practice

Beth is the professional foundation. Everything the business sells traces back to her record:

- Over twenty years teaching, Years 3–12, across Australia, London and Kent

- Fourteen years at St Hilda's School, including Head of St Hilda's@Home — an online learning program built and led well before remote learning was routine

- Deep specialism in the Technologies learning area: Technologies and Innovation Specialist at Coomera Anglican College, Head of Digital Literacy and STEAM Prep–12 at A.B. Paterson College

- Two curriculum authority appointments — three years at ACARA as Curriculum Officer and mentor on the Digital Technologies in Focus project, and a QCAA secondment as Senior Project Officer developing Technologies implementation resources for schools

- Whole-school curriculum leadership: Acting Director then Deputy Director of Teaching and Learning at A.B. Paterson, now Head of Learning Innovation at Hillbrook

- Apple Distinguished Educator

- A warm network across five South-East Queensland independent and Anglican schools

Why this combination is the product Plenty of consultants have been teachers. Plenty have worked at a curriculum authority. Very few have done both, and almost none have done both inside the Technologies learning area — which is simultaneously the area schools are least confident in and the area under most pressure from AI. Beth can speak to a classroom teacher about what an eight-week unit actually takes to deliver, and to a Head of Teaching and Learning about how ACARA intended an achievement standard to be read. That dual fluency is the defensible position. Build the marketing around it.

### Sebastian — the business

You bring what most first-time consultancies lack and cannot buy quickly:

- Running and growing EDS — proven operating discipline, not theoretical business planning

- Commercial systems already understood: contracting, pricing, invoicing, pipeline management, client relationships, cashflow

- The capability to turn a paper diagnostic into a digital product that scales beyond one person's hours

- An outside perspective on education, which is genuinely useful — it keeps the offer framed around the client's problem rather than the practitioner's expertise, which is exactly what the business plan says it wants and exactly what practitioners find hardest to do

Your lack of an education background is not a weakness if you are honest about the role you play. It becomes a weakness the moment either of you implies otherwise in front of a Principal. Section 7 covers how to position it.

## 1.2 What you do not have yet

Accurately: no entity, no ABN, no insurance, no engagement letter, no pricing, no templates, no deliverable product, no client, and no case study. The business plan lists these as “next steps”; the diagnostic exists as thinking rather than an instrument.

This is a normal standing start. It matters only because it dictates order — several of these must exist before a single school is approached.

## 1.3 The constraint that shapes everything

Beth is eight months into a senior, full-time role at Hillbrook. This single fact shapes the first twelve months more than anything else in either document.

The practical consequences:

- Delivery capacity is limited to school holidays, weekends and negotiated leave — realistically a handful of engagement windows per year

- The credibility that makes the practice sellable is currently attached to an employer

- Materials created at work are, in most independent school contracts, the school's intellectual property rather than Beth's

- Approaching schools inside Hillbrook's competitive set carries real professional risk

- The business plan currently lists Hillbrook under “School Experience” alongside past employers — in marketing material that reads as an implied endorsement which has not been given

This does not stop the business It changes the order of operations and the pace, and it makes two things non-negotiable: resolve the employment position before any external activity, and productise early so the practice is not permanently capped by Beth's available hours. Handled well, staying employed through the first year is an advantage — it removes financial pressure, which is what usually forces new consultancies into underpriced, badly scoped work.

# 2. Objectives

Four horizons. Each has a single objective and a set of tests you can answer yes or no to. Vague objectives are the reason most business plans stall at the “next steps” page.

## Horizon 1 — Protect and establish (Months 0–3)

Objective: create a legally sound, insurable vehicle that can accept money, without jeopardising Beth's employment.

| Success test | Evidence it is met |
| --- | --- |
| Entity exists and can invoice | ABN issued, bank account open, first test invoice raised |
| Insurance in place | Professional indemnity and public liability certificates of currency held |
| Employment position resolved | Contract reviewed; disclosure decision made and, if disclosed, confirmed in writing |
| IP boundary documented | Written rule on what may and may not be reused, agreed by both founders |
| Engagement letter ready | Template drafted and reviewed by a lawyer |
| Founders' terms agreed | Signed agreement covering equity, roles, money, IP and exit |
| No premature approaches | Zero schools approached before the above are complete |

## Horizon 2 — Build the minimum sellable product (Months 2–5)

Objective: one diagnostic you can run without improvising, and one deliverable package you can sell off the back of it.

| Success test | Evidence it is met |
| --- | --- |
| Diagnostic V2 exists as an instrument | Question set, respondent protocol, staff survey, rating scale and report template all built |
| Flagship deliverable specified | One package fully scoped, with a defined list of what the school receives |
| Delivery time is known | A dry run has been timed end to end |
| Pricing is set and defensible | Day-rate floor calculated; package prices set; both founders can justify them out loud |
| Both founders can run it | Sebastian can run the survey and analysis; Beth can run the interviews |

## Horizon 3 — Validate (Months 4–9)

Objective: prove the diagnostic produces findings schools will pay to act on.

| Success test | Evidence it is met |
| --- | --- |
| Pilots delivered | Two to three diagnostics run in real schools |
| Conversion demonstrated | At least one pilot converts to a paid deliverable |
| Evidence captured | One written case study with a quantified before-and-after on a single process |
| Credibility assets exist | At least three attributable written testimonials |
| Economics understood | Actual hours per diagnostic measured, so price can be set on evidence |

## Horizon 4 — Establish (Months 9–24)

Objective: a practice with repeat revenue that is not wholly dependent on Beth's availability.

| Success test | Evidence it is met |
| --- | --- |
| Client base | Three or more paying schools |
| Revenue durability | At least one retainer or multi-term engagement |
| Product working | Revenue per delivery hour rising across engagements |
| Asset base building | A template library populated from real engagements, reusable across clients |
| Informed decision point | Beth's employment decision taken against evidence, not optimism |

# 3. Requirements register

Everything that must exist. The Gate column tells you whether it blocks your first paid engagement or can follow it.

Gate key: P0 = must exist before approaching any school. P1 = must exist before first paid engagement. P2 = can follow.

## 3.1 Legal and structural

The first decision is whether to trade through EDS or establish something new. This has tax, liability and brand consequences, so take it to an accountant — but go in with a view.

| Option | Case for | Case against |
| --- | --- | --- |
| Trade through EDS | Fastest. Existing ABN, banking, accounting and insurance relationships. No setup cost. | Commingles an advisory risk profile with your existing business. Brand confusion. Beth has no ownership stake, which is wrong given she is the product. |
| New entity, jointly owned | Reflects the real partnership. Clean liability separation. Survives Beth's employment transition. Can hold IP and be sold or licensed later. | Costs more to establish and run. Requires a shareholders agreement. Needs an accountant's view on structure and tax. |
| Beth as sole trader, Sebastian contracts in | Simplest. Cleanest fit with Beth's personal credibility. | Unlimited personal liability. No shared ownership of what you build together. Hard to unwind later. |
| New entity, Sebastian-controlled | Uses your existing operating experience. Keeps Beth's employment exposure lower on paper. | Ownership does not match contribution. Likely to cause friction once revenue arrives. |

Working recommendation, to test with your accountant A new, jointly-owned company. It gives liability protection, an ownership record that matches contribution, a vehicle that can hold and license the diagnostic IP, and something that continues to work whether or not Beth stays employed. The extra cost and paperwork is the price of not having to restructure in eighteen months. Whatever you choose, do not let the structure decision drift — it blocks the ABN, which blocks the bank account, insurance and every contract.

| Requirement | Why it matters | Owner | Gate |
| --- | --- | --- | --- |
| Business name decided | Still open in the plan. Blocks domain, email, branding, registration. | Both | P0 |
| Structure decided and registered | Determines liability, tax and ownership. | Sebastian | P0 |
| ABN | Cannot invoice a school without one. | Sebastian | P0 |
| Business name registration | Required if trading under anything other than the legal entity name. | Sebastian | P0 |
| Founders' / shareholders agreement | Equity, roles, time and money commitments, decision rights, IP ownership, dispute process, exit. | Both | P0 |
| Engagement letter template | Named in the plan. Scope, deliverables, conditions, disclaimers. | Sebastian, lawyer-reviewed | P1 |
| Standard terms of business | IP licence, confidentiality, limitation of liability, payment terms, cancellation, change requests. | Lawyer | P1 |
| Privacy policy and data handling statement | You will collect staff workload and wellbeing data. Non-optional. | Sebastian | P1 |

## 3.2 Financial

| Requirement | Note | Owner | Gate |
| --- | --- | --- | --- |
| GST registration decision | Threshold-based and it changes. Confirm the current position and the timing of voluntary registration with your accountant. | Accountant | P0 |
| Accounting software and chart of accounts | Set up so engagement profitability can be read per client, not just in total. | Sebastian | P1 |
| Pricing model set | See Section 6. Do not approach schools without it. | Both | P1 |
| Invoicing and payment terms | Schools pay slowly and on their own cycles. Milestone invoicing, not on completion. | Sebastian | P1 |
| Tax and instalment obligations understood | Including implications of a jointly-owned structure for how each of you is paid. | Accountant | P1 |
| Time tracking | So that price can be set from measured effort rather than guesswork. Critical during pilots. | Sebastian | P1 |
| Cashflow runway view | Both of you are employed, so this is low-risk — but establish what you are each willing to invest before revenue. | Both | P0 |

## 3.3 Compliance and risk

| Requirement | Note | Owner | Gate |
| --- | --- | --- | --- |
| Blue Card position confirmed | The general position in Queensland is that contractors whose work is not directed toward children often do not require a blue card — but the exemptions are conditional, teacher registration affects Beth's position, and schools frequently require one contractually regardless. Confirm directly with Blue Card Services rather than inferring. Sebastian should assume he needs one. | Both | P0 |
| Professional indemnity insurance | You are giving advice schools will restructure their processes around. This is the single most important policy. | Sebastian | P1 |
| Public liability insurance | Routinely required as a condition of entering a school site. | Sebastian | P1 |
| Cyber and privacy cover | You will hold staff workload, wellbeing and possibly identifiable survey data. | Sebastian | P1 |
| Run-off cover understood | Professional indemnity claims can arrive after you stop trading. Know the position before you need it. | Broker | P2 |
| Child-safe and visitor policy compliance | Each school will have its own. Expect to sign, induct and comply per site. | Both | P1 |
| Data minimisation practice | Collect the least you need. Anonymise by default. This is both a legal and a trust requirement. | Sebastian | P1 |

## 3.4 Employment and conflict of interest — Beth

This is the highest-risk area in the whole plan and it must be handled before anything external happens. Handled early it is a manageable administrative matter. Handled late, or discovered, it can end a career and the business at the same time.

| Requirement | What it involves |
| --- | --- |
| Read the Hillbrook contract properly | Look specifically for: secondary employment or outside work clauses, restraint of trade, intellectual property assignment, conflict of interest and disclosure obligations. If anything is ambiguous, one hour of employment law advice is cheap insurance. |
| Decide the disclosure position | In most independent schools an early, written, low-key disclosure to the Principal is far safer than being discovered later — and often results in permission with conditions attached. The alternative is carrying a risk you cannot control. |
| Establish a hard IP boundary | Nothing created in Hillbrook time, on Hillbrook systems, or for Hillbrook purposes enters the business. Build every template from scratch, on personal equipment, outside work hours. Keep a dated record showing you did. |
| Fix the current-employer marketing problem | Past employers can be listed factually as career history. A current employer presented as a credential implies endorsement. Remove Hillbrook from any client-facing credential list unless written permission is given. |
| Agree an off-limits school list | Schools in Hillbrook's direct competitive set are off-limits while Beth is employed. Write the list down so there is no case-by-case debate later. |
| Set delivery windows honestly | Map the school calendar and identify the weeks Beth can genuinely deliver. Sell into those windows only. |

## 3.5 Brand and market-facing

| Requirement | Note | Owner | Gate |
| --- | --- | --- | --- |
| Business name and simple identity | Name, logo, colours, document templates. Restrained and professional; schools distrust flashy. | Both | P0 |
| One-page website | Who you are, what you solve, proof, contact. Not a brochure site. It exists so a Principal can check you are real. | Sebastian | P0 |
| Capability statement (one page, PDF) | The leave-behind after the free first meeting. | Both | P1 |
| Testimonials formalised | The six names in the plan converted into written, attributable quotes with permission to publish. | Beth | P1 |
| Case study template | Built before the first pilot so evidence is captured as you go, not reconstructed afterwards. | Sebastian | P1 |
| LinkedIn positioning | Company page, and careful handling of Beth's profile given 3.4. | Both | P2 |

## 3.6 Product and intellectual property

| Requirement | Note | Owner | Gate |
| --- | --- | --- | --- |
| Diagnostic V2 | The instrument, not the description. See Section 4. | Both | P1 |
| Findings report template | The deliverable of the diagnostic and the sales instrument for everything after it. | Both | P1 |
| Action record template | Already well drafted in Matrix V1. Convert to a working form. | Sebastian | P1 |
| Flagship deliverable package | One package, fully specified and costed. Recommend the year-level unit package. | Beth | P1 |
| Template library | Unit plan, assessment task, task-specific rubric, curriculum map, AI assessment scale, AI judgement tool, Digital Technologies policy template. | Beth | P2 |
| IP register | What you own, what is licensed to clients, what is reusable across engagements. Underpins any future licensing model. | Sebastian | P2 |
| Version control and single source of truth | The diagnostic itself asks schools about this. Do not fail your own test. | Sebastian | P1 |

## 3.7 Operational systems — Sebastian's lane

This is where your EDS experience compounds. Most consultancies run on memory and email for two years and then have to rebuild. Build it properly at the start, when there is no data to migrate.

- Pipeline tracking — even a simple board. Every school, every stage, every next action and date

- Document storage with genuine version control and a naming convention

- Diagnostic data capture — digital forms rather than paper, so analysis is not manual transcription

- Anonymous staff survey tooling, with results that aggregate automatically

- Scheduling built around the school calendar, with term dates and delivery windows mapped a year ahead

- Time tracking against engagements, so pricing is evidence-based by the third client

- A controlled template library — one master, versioned, with client copies branched from it

# 4. The diagnostic: from document to product

## 4.1 What V1 is, and what it is not

Matrix V1 is strong thinking. Its central insight — asking how a process actually happens rather than whether a document nominally exists — is exactly right, and it is what separates this from a generic school review. The worked example on Year 5 English is the clearest articulation of the value proposition in either document.

But it is currently a document describing a diagnostic, not a diagnostic. To be delivered repeatably, by two people, at a consistent standard, it needs four layers:

| Layer | What it is | State in V1 |
| --- | --- | --- |
| 1. Instrument | The questions themselves, sequenced, with prompts and follow-ups | Strong — the ten domains are well conceived |
| 2. Protocol | Who is asked, how, in what setting, over how long, with what consent | Missing entirely |
| 3. Analysis | How raw answers become a rated, comparable, defensible picture | Gestured at — the action record fields are a good start |
| 4. Output | What the school receives, and how it converts to further work | Partly sketched — the example outcome shows the shape |

## 4.2 Layer 1 — the instrument

Ten domains is too many for a single engagement. Split into a core set that runs every time and modules that run when indicated by the first conversation.

| Core — run every engagement | Modules — run when indicated |
| --- | --- |
| 1. School direction and expectations 2. Curriculum planning process 3. Unit development and delivery readiness 4. Assessment development 5. Marking, moderation and reporting 8. Workload and working hours | 6. Meetings and collaboration 7. Systems, platforms and resource management 9. Staff capability and confidence 10. AI and digital workload reduction |

Three additions each domain needs:

- Follow-up prompts. “How long does it take?” produces a guess. “Walk me through the last time you did it, start to finish” produces the truth. Every question needs its second-level probe written down, or the diagnostic depends entirely on who is running it.

- Quantification anchors. Offer ranges rather than open numbers, so answers are comparable between respondents and between schools. This is what makes benchmarking possible later.

- An evidence request. Per domain: show me the template, show me where it is stored, show me the last one you completed. What people describe and what exists routinely differ — and the gap is itself a finding.

## 4.3 Layer 2 — the delivery protocol

This is the missing piece, and it is what turns the matrix from a thinking tool into something two different people can run consistently.

### Respondent map

| Respondent | Method | Indicative duration | Why |
| --- | --- | --- | --- |
| Principal or Head of Teaching & Learning | Interview | 60 min | Strategic intent, and what leadership believes is happening |
| Middle leaders (2–3) | Interview | 45 min each | Where policy meets delivery — usually the richest source |
| Classroom teachers (4–6, across phases) | Focus group | 45 min | What actually happens |
| Early career teachers (1–2) | Focus group or interview | 30 min | Onboarding and documentation quality show up here first |
| All teaching staff | Anonymous survey | 10 min | Reach and candour — see below |
| Business manager or IT lead | Interview | 30 min | Only if systems module is in scope |
| Documents | Desk review | — | Curriculum plan, unit templates, assessment templates, storage structure |

The anonymous survey is not optional No teacher will tell a consultant they work Sunday afternoons while sitting in a room with their Head of Department. The interviews give you texture and causation; the anonymous survey gives you scale and honesty. You need both, and the survey is the part that produces the quantified workload figures the value case depends on. It also solves reach: you can hear from an entire staff in ten minutes each, rather than sampling six people and hoping they are representative.

### Psychological safety

Matrix V1 correctly flags that the workload section must not feel like scrutiny. Formalise this rather than leaving it to instinct. Open every session with the same script:

- What this is — a review of processes and systems, not of people

- What it is not — not a performance process, not commissioned to find underperformers

- Who sees what — no individual is identified in any report; survey data is aggregated

- Why they should be candid — the findings determine what the school invests in fixing

- What happens next — and when they will see the outcome

Put the same content in writing as a participant information and consent statement. It protects the staff, the school and you.

## 4.4 Layer 3 — analysis

Findings must be comparable, defensible and repeatable. Three mechanisms do this.

### A two-axis maturity rating

Rate each domain on two independent axes rather than a single score. A single score out of ten is indefensible under challenge and tells a school nothing about what to do.

| Rating | Process maturity | Workload impact |
| --- | --- | --- |
| 1 | Absent — no defined process | Negligible — minimal staff time |
| 2 | Ad hoc — depends entirely on individuals | Low |
| 3 | Emerging — defined but inconsistently applied | Moderate — noticeable but contained |
| 4 | Established — documented and generally followed | High — significant hours, some after-hours |
| 5 | Embedded — documented, followed, reviewed and improved | Severe — routinely requires unpaid additional hours |

Why two axes is the commercial engine A domain that is high maturity but high workload is a different sale from one that is low maturity and low workload. The first needs process simplification; the second needs capability building. Without the second axis you cannot tell them apart, and you will recommend the wrong thing. It also protects the philosophy in the business plan. A school can score well on maturity and still be exhausting its staff — which lets you deliver difficult findings without implying anyone is failing.

### Priority matrix

Plot workload impact against ease of improvement to produce four action categories:

|  | Easy to improve | Hard to improve |
| --- | --- | --- |
| High workload impact | Immediate wins — do first, builds trust and proves value fast | Major projects — scope as staged engagements |
| Low workload impact | Housekeeping — school can self-manage | Deprioritise — name it and move on |

### Time quantification

Convert reported time into annual staff-hours per process. This is the number that makes the value case concrete: “this school spends roughly 400 staff hours a year on duplicated unit planning” is a proposition a Business Manager can act on. “Planning is inefficient” is not.

### Triangulation rule

Never report a finding sourced from a single respondent. Every finding in the report must be corroborated by at least two of: interview, focus group, survey data, document review. Write this rule into the method section of the report — it is what makes the findings survive a defensive leadership team.

## 4.5 Layer 4 — the findings report

The report is both the product of the diagnostic and the sales instrument for everything that follows. Fixed structure:

- Method — what was done, who was consulted, and the limits of the review

- What is working — genuine strengths, named specifically. The plan's philosophy demands this and it buys the licence to say the rest

- The maturity picture — two-axis rating across domains, presented visually

- Priority findings — five to eight maximum, each using the action record fields from Matrix V1

- Quantified workload exposure — annual staff-hours by process

- Recommended sequence — immediate wins first, then structural projects

- What we can provide, and what the school should do itself

Section 7 is the most commercially important part of the report Deliberately recommending things you do not sell — and telling a school plainly which fixes it should handle internally — is what makes the things you do sell credible. It is also a direct expression of the rule already in the business plan: only ever offer a service that proactively benefits the client. Consultants who recommend only their own services get one engagement. Consultants who tell a school what not to buy get referred.

Cap the findings at eight. A report with twenty findings gets filed; a report with six gets acted on.

## 4.6 The conversion funnel

| Stage | What happens | Paid? |
| --- | --- | --- |
| Free first meeting | Scoping conversation. Identify whether there is a real problem worth solving. No pitch. | No — as stated in the plan |
| Diagnostic | Fixed scope, fixed fee. Two days on site plus analysis. | Yes — see below |
| Findings report | Delivered and presented to leadership. | Included in diagnostic |
| Deliverable packages | The actual products — unit packages, policy builds, template libraries, professional learning. | Yes, fixed price per package |
| Review or retainer | Post-implementation review, or ongoing advisory access. | Yes |

The one decision to get right: is the diagnostic free or paid?

The case for free is that it removes friction and generates pipeline. The case for paid is stronger: a school that has paid for a diagnostic will act on it, and a free one gets thanked for and filed. Paying also forces the school to nominate an internal owner, which is the single best predictor of whether anything changes.

Recommendation: keep the first meeting free exactly as the plan states, price the diagnostic, and credit the diagnostic fee against the first deliverable package. That removes the objection without devaluing the work, and it makes the conversion to paid delivery the default rather than a second sale.

## 4.7 Version roadmap

| Version | What it is | When |
| --- | --- | --- |
| V1 | The current document. Thinking, not delivery. | Complete |
| V2 | Deliverable instrument — structured question set with prompts, respondent protocol, anonymous survey, two-axis rating scale, report template. | Required before first pilot |
| V3 | Digital — online survey capture, automated aggregation, generated draft report, emerging cross-school benchmark data. | Months 9–18, Sebastian's build |
| V4 | Licensable — a school, diocese or system runs it themselves under licence, with certification and support. | Months 18+, if the model proves |

Keep V4 in view from day one V4 is where the business stops trading Beth's hours for money — which, given she is employed full-time, is not a distant nicety but the answer to the central constraint identified in Section 1.3. It changes decisions you make now: how you write the instrument, how you store and version it, what the founders' agreement says about IP ownership, and what your engagement terms license to clients versus retain. Build for it early even though you will not sell it for two years.

# 5. Sequenced implementation

Five phases with gates. Each gate is an exit criterion — do not begin the next phase until it is met. The gates exist because the most common failure mode for a new consultancy is approaching the market before it can safely deliver, and then either declining work or delivering badly.

The school calendar dominates everything Budget decisions for the following year are typically made in Term 4. That makes September to November the buying window — approaches landing then reach schools when money is actually being allocated. Late Term 1 and Term 3 are realistic delivery windows; Term 4 and the start of Term 1 are not. Given Beth's availability is already constrained, plan approaches and delivery against this calendar from the outset rather than discovering it in month eight.

## Phase 0 — Decide and protect (Weeks 1–3)

Nothing external happens in this phase. No approaches, no website, no announcement. This phase exists to make everything after it safe.

- Beth reviews her Hillbrook contract in detail; take employment law advice if anything is ambiguous

- Decide the disclosure position and, if disclosing, do it

- Meet an accountant. Decide EDS versus new entity, and joint versus sole ownership

- Agree founders' terms — equity, roles, time, money, IP, decision rights, exit

- Decide the business name

- Write the off-limits school list

Gate: structure decided, employment position clear, name chosen, founders aligned in writing.

## Phase 1 — Establish (Weeks 3–8)

- Register the entity, ABN and business name

- Open the bank account; set up accounting software and chart of accounts

- Obtain insurance quotes and bind professional indemnity, public liability and cyber cover

- Confirm Blue Card position and lodge applications

- Have the engagement letter and standard terms drafted and reviewed

- Write the privacy policy and participant consent statement

- Secure the domain, email and a one-page website

Gate: you could legally, safely and professionally accept a paying client tomorrow.

## Phase 2 — Build the minimum sellable product (Weeks 6–14)

Runs partly in parallel with Phase 1 — Beth builds product while Sebastian handles establishment.

- Build Diagnostic V2 across all four layers (Section 4)

- Build the anonymous staff survey and its aggregation — Sebastian

- Build the findings report template, including the visual maturity picture

- Specify one flagship deliverable package in full. Recommend the year-level unit package — the Matrix already works it through in detail, it addresses the highest-frequency pain point, and its deliverables list is effectively written

- Set pricing (Section 6)

- Dry run: Beth runs the full diagnostic against a hypothetical or friendly school; Sebastian observes and times every component

Gate: you can run a diagnostic end to end without improvising, and you know how many hours it takes.

## Phase 3 — Pilot (Weeks 12–24)

- Select two or three pilot schools from the warm network, deliberately outside Hillbrook's competitive set

- Offer at least one at no or reduced cost, explicitly in exchange for a case study and testimonial — name that trade openly rather than disguising it as a favour

- Run the full diagnostic and deliver the report to leadership in person

- Capture: hours taken, what worked, what schools pushed back on, what they actually bought

- Refine V2 into V2.1 based on what broke

Gate: one written case study with a quantified outcome, three attributable testimonials, and at least one conversion to paid work.

## Phase 4 — First paid engagements (Months 6–12)

- Convert pilot findings into paid deliverable packages

- Approach the wider warm network with a case study in hand — not before

- Track revenue per delivery hour on every engagement

- Build the template library from real engagement outputs rather than speculatively — you will build the wrong templates if you guess

- Establish a referral habit: the plan's closing check-in question is the mechanism; use it every time

Gate: three paying schools, positive unit economics, and a sale you have made the same way more than once.

## Phase 5 — Productise (Months 12–24)

- Build V3 of the diagnostic — digital capture, automated analysis, benchmark data

- Package the most-repeated deliverables into fixed products

- Introduce retainers or per-term advisory arrangements for repeat clients

- Assess licensing potential (V4)

- Revisit Beth's employment decision against actual revenue, pipeline and delivery capacity

Gate: revenue that does not scale linearly with Beth's available hours.

# 6. Commercial model

This section gives you the method rather than the numbers. Any figures quoted here would be invented, and pricing set from invented figures is the fastest way to underprice a practice permanently.

## 6.1 Establish the floor

Take Beth's current total employment package, including superannuation and leave. Divide it by the number of days she could realistically deliver in a year. Then multiply by roughly two and a half to three.

The multiplier covers what employment hides: non-billable time (scoping, proposals, admin, marketing — usually more than half of all working time), overheads, insurance, tax, no paid leave, no sick leave, no superannuation contribution, and the risk premium of irregular income.

Consultants who price from their salary alone go broke slowly and never understand why. That number is your floor, not your price.

## 6.2 Establish the ceiling

The cost-comparison framing already in the business plan is the right instrument, and it is stronger than most consultancies have. Assemble real figures for:

- The cost of recruiting and replacing a teacher

- The cost of onboarding a new teacher into a school's systems and culture

- The value of teaching hours returned to staff, costed at an hourly rate

- The cost of the school building the same capability internally — in staff release time

If a diagnostic identifies several hundred staff hours a year lost to duplicated planning, the value case writes itself and the conversation moves off day rates entirely. This is exactly why the quantification work in Section 4.4 matters commercially.

## 6.3 Revenue lines

| Line | Model | Notes |
| --- | --- | --- |
| Diagnostic | Fixed fee, fixed scope | The entry product. Credit against first package. |
| Deliverable packages | Fixed price per package | Unit packages, policy builds, template libraries, curriculum maps. The core revenue. |
| Professional learning | Per session or per day | The “Using AI” sessions and digital literacy work in Pillar 2. Highest revenue per hour, lowest preparation once built. |
| Retainer | Monthly or per-term | Advisory access. Predictable revenue, and the strongest signal of a healthy practice. |
| Licensing | Annual licence fee | Later. Templates or the diagnostic itself. Where the practice stops being time-for-money. |

## 6.4 Pricing principles

- Fixed price, not hourly, wherever scope can be defined. Schools have budgets and approval processes, not hourly appetites. A fixed price is approvable; an open-ended hourly rate is not.

- Never quote before scoping. The free first meeting exists precisely so you can price properly.

- Price the package, improve margin by getting faster. This is the whole logic of productisation, and it aligns your interests with the client's.

- Milestone invoicing. Schools pay slowly. Invoice on engagement, on report delivery, and on package completion — not once at the end.

- Hold the price. Early discounting to win a first client sets a reference point you will spend two years escaping. Give a pilot away entirely for a case study if you must, but do not discount the standing rate.

# 7. Risk register

| Risk | Severity | Mitigation |
| --- | --- | --- |
| Beth's employment conflict | Severe | Contract review before anything else; early written disclosure; hard IP boundary; documented off-limits school list; remove current employer from credential lists. |
| Key-person dependency on Beth | Severe | Productise from the start; document everything; build toward licensable IP (V3/V4); Sebastian takes every task that does not require education expertise. |
| Capacity collapse — both founders employed | High | Sell only into mapped delivery windows; take fewer engagements than you can win; use school holidays as delivery blocks; say no early rather than late. |
| Partnership breakdown between siblings | High | A written founders' agreement before any money moves. See 7.2. |
| No credibility before the first case study | High | Deliberately pilot at reduced or no cost in exchange for evidence; formalise the six existing testimonials first. |
| Sebastian's education credibility gap | Medium | Position explicitly as the systems, digital and commercial partner. Never imply education expertise. Attend meetings in a clearly defined role. |
| Diagnostic surfaces findings that embarrass leadership | Medium | Report leads with genuine strengths; no individual attribution; agree reporting boundaries in the engagement letter before starting. |
| Staff data privacy breach | Severe | Anonymous survey design; data minimisation; written consent statement; cyber cover; no identifiable data retained after report delivery. |
| Scope creep | Medium | Fixed-scope engagement letters; all changes in writing as a variation; a defined change request process. |
| Seasonality and cashflow | Medium | Align approaches to Term 4 budget cycles; milestone invoicing; both founders employed reduces this materially. |
| Advice liability | Medium | Professional indemnity cover; limitation of liability in standard terms; the advisory-not-directive framing already in the plan. |
| Building the wrong templates first | Low | Build the library from real engagement outputs rather than speculatively. |

## 7.2 Family governance

You are siblings. That is a real advantage — trust, shared history, low transaction cost, and a willingness to work through difficulty that unrelated founders rarely have.

It is also the most common way small partnerships fail badly, because the things that would be explicitly negotiated between strangers get quietly assumed between family. The assumptions only surface when there is money, stress or disagreement — by which point the conversation is much harder and the relationship is what is at stake, not just the business.

Write down, before anything else happens:

- The equity split, and the reasoning behind it

- What each of you commits — in hours per week and in money

- Who decides what alone, and what requires both of you

- How each of you is paid, and when — including whether early revenue is reinvested

- Who owns the intellectual property, and what happens to it if one of you leaves

- What happens if one of you wants out, or wants to stop

- What happens if it does not work

- How you will handle a disagreement neither of you can win

Do this while you like each other It takes an afternoon and a lawyer's review. Every founder who skipped it and later needed it says the same thing. There is also a specific asymmetry here worth naming openly: Beth is the product and Sebastian is the operator. If equity is split on effort in year one it will look wrong by year three, and if it is split on credibility it may feel wrong in year one. Decide deliberately, write down the reasoning, and agree a review point.

# 8. Decision register

Nine decisions that block everything else. If you read nothing else, work through this page together.

| # | Decision | Working recommendation |
| --- | --- | --- |
| D1 | Business name | Decide within two weeks. It blocks domain, registration, branding and every document template. Any reasonable name decided now beats a perfect name decided in month four. |
| D2 | Entity — EDS, new sole trader, or new jointly-owned company | A new jointly-owned company, subject to your accountant's view. Ownership should match contribution, and the entity needs to hold IP and survive Beth's employment transition. |
| D3 | Equity and role split | Decide deliberately with written reasoning and an agreed review point. Beth is the product; Sebastian is the operator. Neither alone makes this work. |
| D4 | Beth's disclosure position at Hillbrook | Disclose early, briefly, in writing, after reading the contract. The alternative is carrying an uncontrollable risk into every client conversation. |
| D5 | Off-limits school list while Beth is employed | Write it down now so there is no case-by-case negotiation under commercial pressure later. |
| D6 | Diagnostic free or paid | Paid, credited against the first deliverable package. Free first meeting stays free, exactly as the plan states. |
| D7 | Which flagship deliverable to build first | The year-level unit package. Matrix V1 already specifies it in full, it addresses the highest-frequency pain point, and its deliverables list is effectively written. |
| D8 | Pilot schools | Two or three from the warm network, outside Hillbrook's competitive set, with at least one explicitly traded for a case study. |
| D9 | Beth's transition decision point | Set a date and define the evidence that would trigger it — pipeline value, retainer count, revenue per delivery hour. Decide on evidence, not on a good month. |

# Appendix A — Pre-launch checklist

Print this. Nothing external happens until every P0 item is complete.

| ☐ | Item | Gate |
| --- | --- | --- |
| ☐ | Hillbrook contract reviewed; disclosure decision made | P0 |
| ☐ | Business name decided | P0 |
| ☐ | Entity structure decided with accountant | P0 |
| ☐ | Founders' agreement signed | P0 |
| ☐ | Off-limits school list written | P0 |
| ☐ | Entity registered; ABN issued | P0 |
| ☐ | Business bank account open | P0 |
| ☐ | Domain and professional email live | P0 |
| ☐ | Blue Card position confirmed; applications lodged | P0 |
| ☐ | Professional indemnity insurance bound | P1 |
| ☐ | Public liability insurance bound | P1 |
| ☐ | Cyber and privacy cover considered | P1 |
| ☐ | Engagement letter and standard terms lawyer-reviewed | P1 |
| ☐ | Privacy policy and participant consent statement written | P1 |
| ☐ | Accounting software and chart of accounts set up | P1 |
| ☐ | Pricing set, with floor calculated | P1 |
| ☐ | One-page website live | P0 |
| ☐ | Capability statement written | P1 |
| ☐ | Six testimonials formalised in writing with permission | P1 |
| ☐ | Diagnostic V2 built across all four layers | P1 |
| ☐ | Anonymous staff survey built and tested | P1 |
| ☐ | Findings report template built | P1 |
| ☐ | Flagship deliverable package specified and costed | P1 |
| ☐ | Full dry run completed and timed | P1 |

# Appendix B — Diagnostic engagement protocol

The one-page operating standard. Refine after each pilot.

| Stage | Activity | Owner | Timing |
| --- | --- | --- | --- |
| Pre-engagement | Free first meeting; scope agreed; engagement letter signed; core and module selection confirmed | Both | Week 0 |
| Preparation | Document request sent; survey distributed to all teaching staff; interview schedule confirmed with the school | Sebastian | Week 1–2 |
| Survey window | Anonymous staff survey open; reminders sent by the school, not by you | Sebastian | Week 2–3 |
| On site — day 1 | Leadership interview; middle leader interviews; document review | Beth | Week 3 |
| On site — day 2 | Teacher focus groups; early career session; systems interview if in scope | Beth | Week 3 |
| Analysis | Survey aggregation; two-axis maturity rating; time quantification; triangulation check; priority matrix | Both | Week 4 |
| Report | Findings report drafted, reviewed by both founders, finalised | Both | Week 4–5 |
| Presentation | Report presented to leadership in person; recommended sequence discussed; proposal for deliverables tabled | Both | Week 5 |
| Follow-up | Closing check-in question; referral request; diary a review point | Beth | Week 6 |

# Appendix C — Questions for your advisers

## For the accountant

- Given two founders, one employed full-time, and an intention to license IP later — which structure and why?

- Should we trade through EDS or establish separately? What are the risk and tax consequences of each?

- What is the current GST registration threshold, and is there a case for registering voluntarily before we reach it?

- How should each of us be paid, given Beth remains employed elsewhere?

- What records do we need from day one that are painful to reconstruct later?

- What are the tax consequences if the entity later licenses the diagnostic rather than delivering services?

## For the lawyer

- Review Beth's employment contract for restraint, secondary employment, IP assignment and disclosure obligations

- Draft or review the founders' / shareholders agreement

- Draft the engagement letter and standard terms, including limitation of liability and IP licensing to clients

- Advise on privacy obligations when collecting staff workload and wellbeing data on a school's behalf

- Who owns the findings report — us or the school — and what may we reuse or publish?

## For the insurance broker

- Professional indemnity cover for advisory work that schools will restructure processes around — what limit is appropriate?

- Public liability at the level schools typically require as a condition of site access

- Cyber and privacy cover given we will hold staff survey data

- How does run-off cover work, and when should we put it in place?

- Does cover extend to both founders, including when one is attending a school in a non-advisory role?

## For Blue Card Services

- Does an education consultant delivering staff-facing advisory work on a school site require a blue card?

- Does Beth's teacher registration exempt her, and does that exemption extend to work outside her employment?

- Does the answer change if children are present on site during the work?

# Appendix D — Diagnostic core and module split

| Domain | Core or module | Rationale |
| --- | --- | --- |
| 1. School direction and expectations | Core | Establishes whether staff effort aligns to leadership intent — frames everything else |
| 2. Curriculum planning process | Core | Where ownership and duplication problems originate |
| 3. Unit development and delivery readiness | Core | The highest-value section; determines whether teachers receive deliverable material |
| 4. Assessment development | Core | Consistently among the largest workload sources |
| 5. Marking, moderation and reporting | Core | The most concentrated after-hours workload in most schools |
| 6. Meetings and collaboration | Module | Run when leadership flags meeting load, or when survey data indicates it |
| 7. Systems, platforms and resource management | Module | Run when multiple platforms or version control problems are evident |
| 8. Workload and working hours | Core | The quantification engine — produces the numbers the value case depends on |
| 9. Staff capability and confidence | Module | Run when the school is considering professional learning investment |
| 10. AI and digital workload reduction | Module | Run when AI policy, academic integrity or assessment risk is a stated concern — increasingly the lead reason for engagement |

A closing observation on Domain 10 AI is currently the fastest route into a school. It is the issue leadership teams feel least equipped for, it carries visible academic integrity risk, and it has a board-level profile that curriculum mapping does not. It is also the domain where Beth's combination of Technologies specialism, curriculum authority background and Apple Distinguished Educator standing is hardest for anyone else to match — and the one where Sebastian's involvement is most credible. Consider leading with it commercially even though the deeper, more durable value sits in Domains 2 to 5.